## Features
Week | Day | Module | Feature | Priority | Complexity | Estimated Hours | Status | Dependencies | Testing Required | API Endpoint
1 | 1-2 | Setup | Create Solution & Project | Critical | Low | 4 | Not Started | None | No | N/A
1 | 1-2 | Setup | Install NuGet Packages | Critical | Low | 2 | Not Started | Project Created | No | N/A
1 | 1-2 | Setup | Create Folder Structure | Critical | Low | 3 | Not Started | Packages Installed | No | N/A
1 | 1-2 | Setup | Create POCO Classes | Critical | Medium | 12 | Not Started | Folder Structure | Yes | N/A
1 | 1-2 | Database | Create DbContext | Critical | High | 16 | Not Started | POCO Classes | Yes | N/A
1 | 1-2 | Database | Initial Migration | Critical | Medium | 6 | Not Started | DbContext | Yes | N/A
1 | 3-4 | Authentication | Identity Framework Setup | Critical | High | 12 | Not Started | Database | Yes | /api/auth/login
1 | 3-4 | Authentication | AuthService Implementation | Critical | High | 16 | Not Started | Identity Setup | Yes | /api/auth/login
1 | 3-4 | Authentication | JWT Token Generation | Critical | Medium | 8 | Not Started | AuthService | Yes | /api/auth/refresh
1 | 5-7 | User Management | Generic Repository | Critical | Medium | 8 | Not Started | Authentication | Yes | N/A (MVC)
1 | 5-7 | User Management | User Repositories | Critical | Medium | 12 | Not Started | Generic Repo | Yes | N/A (MVC)
1 | 5-7 | User Management | UserService Implementation | Critical | High | 16 | Not Started | User Repos | Yes | N/A (MVC)
1 | 5-7 | User Management | Bulk Import (Excel) | High | High | 12 | Not Started | UserService | Yes | N/A (MVC)
1 | 5-7 | User Management | Face Photo Upload | Critical | High | 16 | Not Started | UserService | Yes | N/A (MVC)
2 | 8-9 | Academic Structure | Department CRUD | Critical | Medium | 8 | Not Started | User Management | Yes | N/A (MVC)
2 | 8-9 | Academic Structure | Level CRUD | Critical | Medium | 6 | Not Started | Departments | Yes | N/A (MVC)
2 | 8-9 | Academic Structure | Section CRUD | Critical | Medium | 6 | Not Started | Levels | Yes | N/A (MVC)
2 | 8-9 | Academic Structure | Group CRUD | Medium | Low | 4 | Not Started | Sections | Yes | N/A (MVC)
2 | 10-11 | Course Management | Course CRUD | Critical | Medium | 12 | Not Started | Academic Structure | Yes | N/A (MVC)
2 | 10-11 | Course Management | Term Management | Critical | Medium | 8 | Not Started | Courses | Yes | N/A (MVC)
2 | 10-11 | Course Management | Course Offerings | Critical | High | 16 | Not Started | Course + Term | Yes | N/A (MVC)
2 | 10-11 | Course Management | Student Enrollment | Critical | Medium | 8 | Not Started | Offerings | Yes | N/A (MVC)
2 | 10-11 | Course Management | Prerequisite Handling | High | Medium | 6 | Not Started | Courses | Yes | N/A (MVC)
2 | 12-13 | Timetable | Timetable Generation Algorithm | Critical | Very High | 40 | Not Started | Academic Structure + Offerings | Yes | N/A (MVC)
2 | 12-13 | Timetable | Conflict Detection | Critical | High | 16 | Not Started | Timetable Gen | Yes | N/A (MVC)
2 | 12-13 | Timetable | Manual Adjustments | High | Medium | 8 | Not Started | Timetable Gen | Yes | N/A (MVC)
2 | 12-13 | Timetable | Timetable Publishing | Critical | Medium | 6 | Not Started | Timetable Gen | Yes | N/A (MVC)
2 | 12-13 | Timetable | Room Assignment | High | High | 12 | Not Started | Timetable Gen | Yes | N/A (MVC)
2 | 14 | Sessions | Session API Endpoints | Critical | Medium | 8 | Not Started | Timetable Published | Yes | /api/sessions/today
2 | 14 | Sessions | Session Service | Critical | Medium | 8 | Not Started | Sessions | Yes | /api/sessions/{id}
2 | 14 | Sessions | Today's Schedule | Critical | Low | 4 | Not Started | Sessions | Yes | /api/sessions/today
2 | 14 | Attendance | Attendance Repository | Critical | Medium | 8 | Not Started | Sessions | Yes | N/A
2 | 14 | Attendance | Attendance Service | Critical | High | 12 | Not Started | Session Service | Yes | N/A
3 | 15-16 | Quizzes | Quiz Creation | High | High | 24 | Not Started | Courses | Yes | N/A (MVC)
3 | 15-16 | Quizzes | Quiz Questions (MCQ) | High | Medium | 16 | Not Started | Quiz Creation | Yes | N/A (MVC)
3 | 15-16 | Quizzes | Quiz Assignment | High | Medium | 8 | Not Started | Quiz + Offering | Yes | N/A (MVC)
3 | 15-16 | Quizzes | Auto-Grading Algorithm | Critical | Very High | 32 | Not Started | Quiz Questions | Yes | N/A (Auto)
3 | 15-16 | Quizzes | Quiz API Endpoints | Critical | High | 16 | Not Started | Quiz Assignment | Yes | /api/quizzes/*
3 | 17-18 | Face Recognition | Face Recognition Package Wrapper | Critical | Very High | 40 | Not Started | User Registration | Yes | N/A (Service)
3 | 17-18 | Face Recognition | Face Embedding Storage (Base64) | Critical | High | 12 | Not Started | Face Package | Yes | N/A (DB Field)
3 | 17-18 | Face Recognition | Face Verification | Critical | Very High | 24 | Not Started | Face Embedding | Yes | N/A (Service)
3 | 17-18 | Attendance | Face Check-In API | Critical | Very High | 24 | Not Started | Face Verification + Sessions | Yes | /api/attendance/check-in
3 | 19-21 | Grading | Grade Components Configuration | High | Medium | 12 | Not Started | Offerings | Yes | N/A (MVC)
3 | 19-21 | Grading | Grade Entry | High | Medium | 16 | Not Started | Grade Components | Yes | N/A (MVC)
3 | 19-21 | Grading | Final Grade Calculation | Critical | High | 24 | Not Started | Grades Entered | Yes | N/A (Service)
3 | 19-21 | Grading | Letter Grade Conversion | Critical | High | 12 | Not Started | Final Grades | Yes | N/A (Service)
3 | 19-21 | Grading | GPA Calculation (4.0 Scale) | Critical | Very High | 32 | Not Started | GPA Calculation | Yes | /api/grades/gpa
3 | 19-21 | Grading | Transcript Generation (PDF) | High | High | 16 | Not Started | Grades Complete | Yes | /api/grades/transcript
4 | 22-23 | Materials | Material Upload | Medium | Medium | 8 | Not Started | Offerings | Yes | /api/materials/*
4 | 22-23 | Materials | Material Folders | Medium | Low | 4 | Not Started | Materials | Yes | N/A (MVC)
4 | 22-23 | Materials | Material API | Medium | Low | 4 | Not Started | Materials | Yes | /api/materials/*
4 | 24-25 | Reports | Attendance Reports | Medium | Medium | 12 | Not Started | Attendance System | Yes | N/A (MVC)
4 | 24-25 | Dashboard | Admin Dashboard with Stats | Medium | Medium | 12 | Not Started | All Features | Yes | N/A (MVC)
4 | 26-30 | Testing | Unit & Integration Tests | High | High | 40 | Not Started | All Features | Yes | N/A
4 | 26-30 | Deployment | Production Deployment | Critical | High | 24 | Not Started | Testing Complete | Yes | N/A

## Summary
Metric | Value
Total Features | 55
Total Estimated Hours | 751
Duration (Days) | 30
Week 1 Hours | 143
Week 2 Hours | 196
Week 3 Hours | 308
Week 4 Hours | 104
Critical Priority Features | 38
High Priority Features | 11
Medium Priority Features | 6
Very High Complexity Features | 6
High Complexity Features | 18
Features Requiring Testing | 52